## Sheet1
[36 empty] | Status |  |  |  | Status
[14 empty] | NAME |  | Andrea Bolin | [15 empty] | MONTH / YR |  |  | March 2023 | HAWKSLEY | Team | AS / AAB / VV / WYL / CF |  | COURTENAY | Team | AS / AAB / CF
PROJECT | [35 empty] | Focus | IFC CAD Bases to Consults | Intensive Internal Review, Coordination & Annotation | Stair C & D | Focus | Driveway | Waiting on DrivewayPaver Completion
NO. | NAME | WORK | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | TOTAL | DESCRIPTION / COMMENTS |  |  | Intensive REVIT Review, Cleanup & Learning | Crane Pad & slab opening coordiantion
|  | CODE | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F |  |  |  |  | Intensive Consultant Review & Coordination | Water Meter chamber location
1508 | COURTENAY | CODE: OCC; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X | 0 | Post Occupancy - PAVERS |  | BP Revisions | Response to Final round of DWV Inquiries | Site & Drainage
1712 | HAWKSLEY | IFT/IFC | 0.5 |  |  | X | X | 0.5 |  |  | 0.5 |  | X | X | 0.5 |  |  |  | 1 | X | X |  |  | 1.5 | 0.5 | 0.5 | X | X | 0.5 |  | 0.5 |  | 0.5 | 7 | Proj Admin (Billing, Printing, Uploads, Sched, General) |  | EXTRA | Purchaser Unit change 601 | Walls & Drops
1712 | HAWKSLEY | IFT/IFC | 1.5 | 3 | 1.5 | X | X | 0.5 | 2.5 | 1.5 | 0.5 | 0.5 | X | X |  | 0.5 | 1 | 2 | 1.5 | X | X | 2.5 | 2.5 | 0.5 | 1.5 | 2 | X | X | 0.5 | 0.5 | 0.5 | 2.5 | 0.5 | 30 | Internal Meetings / Coordination (Vlad / Wai Yan / Al) |  |  |  | E - Panels, Emerg distribution rm
1712 | HAWKSLEY | CODE: IFT/IFC; W: 2.5; T: 1; S: X; S: X; M: 2.5; T: 4; S: X; S: X; S: X; S: X; T: 3; W: 1; S: X; S: X; M: 2; T: 2; W: 1; F: 1 | 20 | Consultant / Client Meetings | Milestones |  |  | P - Roof, TH Terrace & autocourt Drains
1712 | HAWKSLEY | IFT/IFC |  | 1 | 4 | X | 2 | 3 |  | 3 | 6.5 | 4 | X | 2 |  | 2.5 | 2 | 6.5 | 3.5 | 2 | 3 | 4 | 2 |  | 2 | 4 | 2 | 3 | 4.5 | 5 | 5 | 5 | 4.5 | 86 | IFC Building Drawings, Coord | 2023-03-08 | IFC CAD Bases | Dated 230224 / Uploaded 230308 | P - Wall thkness & panel | Milestones
1712 | HAWKSLEY | CODE: BP; T: 1; F: 0.5; S: X; S: X; T: 0.5; F: 1; S: X; S: X; M: 2.5; S: X; S: X; W: 1; T: 1; S: X; S: X | 7.5 | BP Comments + Changes | 2023-03-13 | BP Responses to DWV | Dated 230313 | M - In slab duct coordiantion w/ S & Mullions | DONE | Occupancy | Dated 230120
1712 | HAWKSLEY - Spec | CODE: IFT; W: 1.5; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X | 1.5 | Spec - Res | 2023-03-23 | BP Responses to DWV - Final | Dated 230323 | M / S - Duct / Vent openings
1712 | HAWKSLEY | CODE: EXTRA; S: X; S: X; S: X; S: X; S: X; S: X; M: 1; W: 1; T: 3; S: X; S: X | 5 | Extra - Purchaser customization / insurer Inquiries | 2023-04-10 | BP Issuance | Imminent (TBC) | LS / A - Coordination w. Arch
1712A | HAWKSLEY - Amen | CODE: IFT; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X | 0 | IFT Amenity - Drawings + Coord / Admin | 2023-04-17 | IFC DRAFT | Dated 230417 / Uploaded | LS / P - Coordination w. PC
1712A | HAWKSLEY - Amen | [32 empty] | 0 | BP Amenity - Drawings + Coord | 2023-05-08 | IFC Below Grade | Dated 230508 / Uploaded | LS - Coord w. Civ & Geo (esp N Bank Retaining) | bar: CODE to F
1712A | HAWKSLEY - Amen | CODE: IFT; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X | 0 | Spec - Amenity | 2023-07-03 | IFC Above Grade | Dated 230703 / Uploaded | REVIT - Graphics, Modelling, Cleanup & Learning
1712 | HAWKSLEY - RVT | S: X; S: X; S: X; S: X; S: X; S: X; S: 1; S: 2 | 3 | REVIT model cleanup + Learning | DONE - 02-23 | Re-IFT 1 | Dated 230224 / Uploaded 230308
| subtotal |  | 6 | 6 | 6 | 0 | 2 | 6.5 | 7 | 4.5 | 7.5 | 5.5 | 0 | 2 | 3 | 3 | 3 | 8.5 | 6 | 2 | 3 | 7.5 | 7.5 | 5 | 8 | 6.5 | 3 | 5 | 7.5 | 7.5 | 7 | 7.5 | 6.5 | 160
STAT. HOLIDAY | [33 empty] | 0
ADMIN /GENERAL |  | W: 0.5; F: 0.5; W: 2; W: 0.5; W: 0.5; W: 0.5 | 4.5 | Filing, Cleanup/Move, Time, Other
PROMOTION | [33 empty] | 0
PROFESSIONAL DEVELOPMENT | [33 empty] | 0 |  | Other
PROFESSIONAL DEV - UNPAID | [35 empty] | 1 | bar: F
ILLNESS | [33 empty] | 0
VACATION | [33 empty] | 0 | Days Remaining: 5 (2020) / 25 (2021) / 25 (2022)
OTHER - REVIT Standards |  | F: 1; M: 3; W: 2.5; T: 0.5; F: 1; F: 1 | 9 | Meetings / Organization / Review / Development | 9
OTHER - REVIT Details | [33 empty] | 0 |  | 0
OTHER - Std Assbl's Dets Gen Notes | [33 empty] | 3 |  | 3 | bar: W; T to W
OTHER - Contract Admin | [35 empty] | 2 | bar: W; F
OTHER - Specification | [33 empty] | 2 |  | 2 | bar: T; T
OTHER - Sustainability |  | T: 1; M: 1; T: 1.5 | 3.5 | Meetings + Prep / K drive cleanup / other uploads for site | 3.5
OTHER - Software | [34 empty] | Air Table / Filemaker review / Sefaira demo | 0
OTHER - Associate + Partner mtgs | [33 empty] | 1 |  | 1 | bar: T
OTHER - Please specify |  | T: 0.5; W: 1; F: 1.5; W: 2 | 5 | Reem Marie Discussion / Student Sam
total |  |  | 7.5 | 8 | 7.5 | 0 | 2 | 7.5 | 8 | 7.5 | 7.5 | 7.5 | 0 | 2 | 6 | 6 | 8 | 10 | 7.5 | 2 | 3 | 7.5 | 7.5 | 7.5 | 8 | 7.5 | 3 | 5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 188 |  | 21.5
WORK CODES:
D | Pre-DP or schematic design / investigation | F: ADM; S: Construction administration / site services; W: Enter no of paid days in square; T: 23 | 172.5
DP | DP Drawings | F: EXTR; S: Extra services beyond contract - SEE EXTRA SERVICE FORM
BP | Building permit | F: SPEC; S: Specification; W: Flextime (Timeoff) this month | 15.5 | Specify for each project above
WD | Working drawings | F: TEND; S: Tendering phase
MOD | Model Making | F: CON; S: Construction phase - drawing details during construction and; W: Flextime (Timeoff) beginning of month | 544.5
MK | Marketing | S: coordination of these that should have been done before tender
|  | W: Flextime (Timeoff) end of month | 560
Note on T7: Andrea Bolin: filing / time -.5 NS call - .5
Note on Y7: Andrea Bolin: Plots & Send to TR / TR Inquiry
Note on D8: Andrea Bolin: VV - .5 WYL - 1
Note on E8: Andrea Bolin: VV - Site, TH stairs & amenity Bridge - 1 WYL - units, panel coordination, other coordination - 2
Note on F8: Andrea Bolin: VV - .5 WYL - 1
Note on I8: Andrea Bolin: VV
Note on J8: Andrea Bolin: VV - Site, TH stairs & amenity Bridge - 1 WYL - units, panel coordination, other coordination - 1.5
Note on K8: Andrea Bolin: VV - .5 WYL - 1
Note on R8: Andrea Bolin: WYL
Note on S8: Andrea Bolin: VV - .5 WYL - 1.5
Note on T8: Andrea Bolin: VV - .5 WYL - 1
Note on W8: Andrea Bolin: VV - morning mtg & TH Stairs & Amenity Bridge)
Note on X8: Andrea Bolin: VV - .5 WYL - 1 Gen WYL - 1 Plumb
Note on Z8: Andrea Bolin: VV - .5 WYL - 1
Note on AA8: Andrea Bolin: VV - .5 WYL - 1.5
Note on AG8: Andrea Bolin: VV - 1 WYL - 1.5
Note on D9: Andrea Bolin: NS - Wetlands ROW IFC/ IFT Kickoff meeting
Note on E9: Andrea Bolin: NS - BP Responses
Note on I9: Andrea Bolin: NS - IFT-1 Upload Audit - 1 North retaining - VDZ / Geo … - 1.5
Note on J9: Andrea Bolin: IFT / IFC consultant meeting - staggererd
Note on X9: Andrea Bolin: Staggerred All Consultant Coordiantion mtg
Note on Y9: Andrea Bolin: PC-p / VDZ - Site Drainage
Note on AD9: Andrea Bolin: GS/PC - 1 (Ducts & Vents @ S Core elements) PC - 1 (In slab Ducts)
Note on AE9: Andrea Bolin: Consult Team mtg
Note on AF9: Andrea Bolin: Paver spec
Note on AH9: Andrea Bolin: NS - IFC Background status
Note on S10: Andrea Bolin: - Plumbing Drain/Wall & BBQ Coord - 4.5 - Wendell - .5 - BB review consults - 2
Note on AC10: Andrea Bolin: Crane base update / coord
Note on E11: Andrea Bolin: call w. NS / GHL
Note on P11: Andrea Bolin: BP responses
Note on W13: Andrea Bolin: - BL - Insurance inquiries about extent of insulation & poly
Note on Y13: Andrea Bolin: discussions w/ BL/AS
Note on Z13: Andrea Bolin: - Purchaser - discussions w/ WYL - BL - Insurance inquiries about extent of insulation & poly
Note on M23: Andrea Bolin: Challenges of Blindside Waterproofing L&L
Note on P26: Andrea Bolin: AAB - Gen Notes & Ptotocols WYL - Filters HS - Doors / Naming
Note on R26: Andrea Bolin: - Outline REVIT goals - 1 - Fariba mtg - 2
Note on Q28: Andrea Bolin: Door schedule info for GM / Signage
Note on Q34: Andrea Bolin: RM - Message to partners
Note on R34: Andrea Bolin: Sam - Hawksley General
Note on T34: Andrea Bolin: Sam - Roof Detail Mech
Note on Y34: Andrea Bolin: Reem