## Sheet1
[36 empty] | Status |  |  |  | Status
[14 empty] | NAME |  | Andrea Bolin | [15 empty] | MONTH / YR |  |  | April 2023 | HAWKSLEY | Team | AS / AAB / VV / WYL / CF |  | COURTENAY | Team | AS / AAB / CF
PROJECT | [35 empty] | Focus | IFC DRAFT | Intensive Internal Review, Coordination & Annotation |  | Focus | Driveway | Waiting on DrivewayPaver Completion
NO. | NAME | WORK | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | TOTAL | DESCRIPTION / COMMENTS |  |  | P3 below slab coordination / Site drainage
|  | CODE | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S |  |  |  |  | EXTRA | Discussion re Changes to corridor pressurization / ERV
1508 | COURTENAY | CODE: OCC; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X |  | 0 | Post Occupancy - PAVERS |  |  |  | Site & Drainage
1712 | HAWKSLEY | IFC | X | X | [5 empty] | X | X |  |  | 0.5 |  | 0.5 | X | X | 1.5 | 0.5 | 0.5 |  |  | X | X |  | 0.5 | 1 | 1 |  | X | X |  | 6 | Proj Admin (Billing, Printing, Uploads, Sched, General) |  | OTHER INFO | AAB working remotely: Apr 19-26
1712 | HAWKSLEY | IFC | X | X | 2 | 2 | 2 | 1.5 |  | X | X | 2 | 1 | 3.5 | 1 | 1 | X | X | 1 | 2.5 | 0.5 | 1.5 | 1.5 | X | X | 0.5 |  |  | 1 | 3 | X | X |  | 27.5 | Internal Meetings / Coordination (Vlad / Wai Yan / Al) |  |  |  | E - Panels, Emerg distribution rm
1712 | HAWKSLEY | IFC | X | X |  | 4 |  | 0.5 |  | X | X |  | 3 |  |  |  | X | X |  |  |  | 1 |  | X | X | 2 | 0.5 |  | 2 | 1 | X | X |  | 14 | Consultant / Client Meetings | Milestones |  |  | P - Roof, TH Terrace & autocourt Drains
1712 | HAWKSLEY | IFC | X | 2 | 4.5 |  | 3 | 3 |  | X | X | 3 | 2.5 | 2 | 6.5 | 5 | 2 | 2 | 5 | 3.5 | 4.5 | 5 | 4 | X | X | 5 | 1.5 | 1 | 2.5 | 3.5 | 2 | 2 |  | 75 | IFC Building Drawings, Coord | 2023-03-08 | IFC CAD Bases | Dated 230224 / Uploaded 230308 | P - Wall thkness & panel | Milestones
1712 | HAWKSLEY | [32 empty] | 0 | BP Comments + Changes | 2023-03-13 | BP Responses to DWV | Dated 230313 | M - In slab duct coordiantion w/ S & Mullions | DONE | Occupancy | Dated 230120 | bar: CODE to S
1712 | HAWKSLEY - Spec | CODE: IFC; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X |  | 0 | Spec - Res | 2023-03-23 | BP Responses to DWV - Final | Dated 230323 | M / S - Duct / Vent openings
1712 | HAWKSLEY | CODE: EXTRA; S: X; S: X; S: X; S: X; F: 1; S: X; S: X; W: 1; F: 1; S: X; S: X; T: 1; S: X; S: X |  | 4 | Extra - ERV's / Purchaser customizations | 2023-05-01 | BP Issuance | Dated 230501 - Exact day TBC) | LS / A - Coordination w. Arch
1712A | HAWKSLEY - Amen | CODE: IFT; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X |  | 0 | IFT Amenity - Drawings + Coord / Admin | 2023-04-17 | IFC DRAFT | Dated 230417 / Uploaded 230419 | LS / P - Coordination w. PC
1712A | HAWKSLEY - Amen | [32 empty] | 0 | BP Amenity - Drawings + Coord | 2023-05-08 | IFC BG / Progress |  | LS - Coord w. Civ & Geo (esp N Bank Retaining) | bar: CODE to S
1712A | HAWKSLEY - Amen | CODE: IFT; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X |  | 0 | Spec - Amenity | 2023-05-12 | IFC BG IFC DRAFT-1 |  | REVIT - Graphics, Modelling, Cleanup & Learning
1712 | HAWKSLEY - RVT | S: X; S: X; M: 1; T: 1; S: X; S: X; M: 2; T: 1; S: X; S: X; T: 1; F: 1; S: X; S: X; S: X; S: X |  | 7 | REVIT model cleanup + Learning | 2023-05-26 | IFC BG IFC
| subtotal |  | 0 | 2 | 7.5 | 6 | 5 | 6 | 0 | 0 | 0 | 7 | 7.5 | 6 | 7.5 | 7.5 | 2 | 2 | 7.5 | 7.5 | 6.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 2.5 | 2 | 7.5 | 7.5 | 2 | 2 | 0 | 133.5
STAT. HOLIDAY |  | F: 7.5 |  | 7.5 |  | 2023-07-03 | IFC Above Grade | Dated 230703 / Uploaded
ADMIN /GENERAL |  | W: 2.5; M: 0.5; W: 0.5; W: 1 |  | 4.5 | Filing, Cleanup/Move, Time, Other | DONE - 02-23 | Re-IFT 1 | Dated 230224 / Uploaded 230308
PROMOTION | [33 empty] | 0
PROFESSIONAL DEVELOPMENT | [33 empty] | 0 |  | Other
PROFESSIONAL DEV - UNPAID | [35 empty] | 0
ILLNESS | [33 empty] | 0
VACATION | [33 empty] | 0 | Days Remaining: 5 (2020) / 25 (2021) / 25 (2022)
OTHER - REVIT Standards | [33 empty] | 0 | Meetings / Organization / Review / Development | 0
OTHER - REVIT Details | [33 empty] | 0 |  | 0
OTHER - Std Assbl's Dets Gen Notes | [33 empty] | 1 |  | 1 | bar: W
OTHER - Contract Admin | [35 empty] | 0
OTHER - Specification | [33 empty] | 0 |  | 0
OTHER - Sustainability | [33 empty] | 0 | Meetings + Prep / K drive cleanup / other uploads for site | 0
OTHER - Software | [34 empty] | Sefaira demo | 1 | bar: T
OTHER - Associate + Partner mtgs |  | T: 2 |  | 2 |  | 2
OTHER - Please specify |  | T: 1.5 |  | 1.5 | Student Sam Interview
total |  |  | 0 | 2 | 7.5 | 9 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 2 | 2 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 2.5 | 2 | 7.5 | 7.5 | 2 | 2 | 0 | 150 |  | 4
WORK CODES:
D | Pre-DP or schematic design / investigation | M: ADM; W: Construction administration / site services; S: Enter no of paid days in square; S: 20 |  | 150
DP | DP Drawings | M: EXTR; W: Extra services beyond contract - SEE EXTRA SERVICE FORM
BP | Building permit | M: SPEC; W: Specification; S: Flextime (Timeoff) this month |  | 0 | Specify for each project above
WD | Working drawings | M: TEND; W: Tendering phase
MOD | Model Making | M: CON; W: Construction phase - drawing details during construction and; S: Flextime (Timeoff) beginning of month |  | 560
MK | Marketing | W: coordination of these that should have been done before tender
|  | S: Flextime (Timeoff) end of month |  | 560
Note on Q7: Andrea Bolin:
Note on T7: Andrea Bolin: IFC draft - consultant uploads - ftp site & BB
Note on U7: Andrea Bolin: .5 - client comm
Note on AD7: Andrea Bolin: .5 - AS re BL comments .5 - NS
Note on M8: Andrea Bolin: VV - embeds / Site WY
Note on O8: Andrea Bolin: VV - 2 site VV - .5 embeds WY - .5 TH stairs WY - .5 TH slabs
Note on U8: Andrea Bolin: VV - .5 Amenity Bridge WY - 1.5 Drawing review CF - .5 meetings, info transfer
Note on V8: Andrea Bolin: .5 -VV - site
Note on W8: Andrea Bolin: .5 - VV - site 1 - WY
Note on X8: Andrea Bolin: VV - No power 1.5 - WY
Note on AA8: Andrea Bolin: CF
Note on AD8: Andrea Bolin: WY VV
Note on AE8: Andrea Bolin: WY - 2.5 VV - .5
Note on G9: Andrea Bolin: 2.5-3 Retaining Walls Prep 3-4.5 Retaining Walls Mtg 4.5-5 iCAD mtg 5-6.5 mtg minutes
Note on I9: Andrea Bolin: NS call to f/u on items
Note on N9: Andrea Bolin: Team progress review - 2.5-5.5
Note on W9: Andrea Bolin: Excavation mtg
Note on AA9: Andrea Bolin: Excavation & Blasting - 1 Zoom Meeting - PC-P - 1
Note on AD9: Andrea Bolin: Teams - Team mtg
Note on AE9: Andrea Bolin: Zoom Meeting - PC-P
Note on E10: Andrea Bolin: clean up grids & slabs
Note on F10: Andrea Bolin: clean up grids & slabs
Note on H10: Andrea Bolin: model reviww & updates /review of mtl items & OH doors
Note on N10: Andrea Bolin: coord w. VDZ Bag walls & site CAD review Metals visibility
Note on O10: Andrea Bolin: Site model
Note on P10: Andrea Bolin: screens site L4 east planters slabs drop ceilings East garage doghouse East Garage door openrer coord w. supplier water meter chamber
Note on Q10: Andrea Bolin: in-slab ducts / coord w. CL Water meter chamber Site drainage
Note on R10: Andrea Bolin: site
Note on S10: Andrea Bolin: site
Note on T10: Andrea Bolin: Rooftop ERV's - pre revision Dims views completion towards IFC draft East Garage door opener coord
Note on U10: Andrea Bolin: .5 - Built Green doc from E3E - file & distribute .5 - NWS - request to upload Sprinkler dwgs .5 - NE - Views review 2 - Dwgs towards IFC Draft
Note on V10: Andrea Bolin: Review DWV Garbage pickup doc from NS Slab plans esp P3 re Excavation audit Thurs
Note on W10: Andrea Bolin: Slab plans esp P3 re Excavation audit Thurs Coord w. ICAD Coord w. PC-p re drains btwn slabs & ftgs Add struct ftgs
Note on X10: Andrea Bolin: Slab plans esp P3 re Excavation audit Thurs Add struct ftgs
Note on AA10: Andrea Bolin: Slab plans esp P3 re Excavation audit last Thurs Add struct ftgs Elevator core ftgs Amenity Slab
Note on AB10: Andrea Bolin: Amenity slab drains (BG or Amenity?)
Note on AC10: Andrea Bolin: Amenity slab drains (BG or Amenity?)
Note on AD10: Andrea Bolin: .5 - BL comments review .5 - Column review & inquiry to GS .5 - Duct review & coord .5 - Site Drains .5 - P3 SOG
Note on AE10: Andrea Bolin: Siber mtg setup & details request Coord re P3 slab Mech coord re Sumps
Note on AF10: Andrea Bolin: Tracker review / Update progress towards re IFC draft
Note on AG10: Andrea Bolin: progress towards re IFC draft
Note on Q13: Andrea Bolin: Purchaser customization
Note on V13: Andrea Bolin: ERV revs - review PC update plans
Note on X13: Andrea Bolin: Rooftop VRF Zoom Meeting - BL / PC / RWA
Note on AD13: Andrea Bolin: ERV revs
Note on M17: Andrea Bolin: revit w VV
Note on N17: Andrea Bolin: Revit - site modelling
Note on U17: Andrea Bolin: WY - 1 REVIT protocols
Note on X17: Andrea Bolin: revit - speed & views
Note on H20: Andrea Bolin: Time keeping / review of student Sams work for review
Note on G32: Andrea Bolin: Safaira review w. Saphair folks - not now, will review relevance to software in the future
Note on I34: Andrea Bolin: Student Sam interview & prep