## Sheet1
[14 empty] | NAME |  | Andrea Bolin | [15 empty] | MONTH / YR |  |  | October 2023
PROJECT
NO. | NAME | WORK | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | TOTAL | DESCRIPTION / COMMENTS |  |  |  | 1712 |  | HAWKSLEY |  |  |  |  | Vacation Summary
|  | CODE | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | [5 empty] | Milestones |  |  |  | Team |  |  | 2020 | 2021 | 2022 | 2023
0 | bar: S; S to S; S to S; S to S; S to S
1712 | HAWKSLEY | CODE: ADM; S: X; T: 1; S: X; S: X; T: 1; S: X; S: X; T: 1; S: X; S: X; S: X; S: X | 3 | Admin (Billing, Printing, Uploads, Sched, General) |  |  |  | DONE - 02-23 |  | Re-IFT 1 | Dated 230224 / Uploaded 230308 | AS | Design Architect / Signing Partner |  | 3 | 13 | 25 | 25 | Start of Month
1712 | HAWKSLEY | CODE: ADM; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X | 0 | Internal Meetings / Coordination (CF / RM / Consult docs) |  |  |  | 2023-03-08 |  | IFC CAD Bases | Dated 230224 / Uploaded 230308 | AAB | Project Manager / CA Support |  | 3 | 10 |  |  | This Month
1712 | HAWKSLEY | ADM | X |  | 2 |  | 1 | 3 | X | X |  |  |  | 1 | 0.5 | X | X |  | 3 |  |  | 1 | X | X |  |  | 0.5 |  | 2 | X | X | 1 | 2 | 17 | Consultant / Client Meetings |  |  |  | 2023-03-13 |  | BP Responses to DWV | Dated 230313 | CF | CA - Site | CF - Started joining mtgs -Feb | 0 | 3 | 25 | 25 | End of Month
1712 | HAWKSLEY | ADM | X |  | 4.5 | 5 | 6.5 | 4.5 | X | X |  | 6 | 6.5 | 5.5 | 7 | X | X | 7.5 | 2 | 4 | 6.5 | 6.5 | X | X | 7.5 | 6.5 | 6 | 7.5 | 5.5 | X | X | 6.5 | 3 | 114.5 | CA |  |  |  | 2023-03-23 |  | BP Responses to DWV - Final | Dated 230323 | RM | CA - Office & Suppot
1712 | HAWKSLEY - Spec | CODE: SPEC; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X | 0 | Spec - Res |  |  |  | 2023-05-01 |  | BP Issuance | Dated 230501 - Exact day TBC) | RJ | Production Support | RJ - Started May 8th
1712 | HAWKSLEY | CODE: EXTR; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X | 0 | EXTRA |  |  |  | 2023-04-17 |  | IFC DRAFT | Dated 230417 / Uploaded 230419 | SM | Production Support / REVIT Template | SM - Started June 9th
[34 empty] | 0 |  |  |  |  | 2023-05-08 |  | IFC BG / Progress | bar: CODE to S; T to S; T to S; T
1712A | HAWKSLEY - Amen | CODE: BP rev; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X | 0 | Amenity - Admin (Billing, Printing, Uploads, Sched, General) |  |  |  | 2023-05-12 |  | IFC BG IFC DRAFT-1 | Dated 230512 / Uploaded 230515 | RJ | X
1712A | HAWKSLEY - Amen | CODE: BP rev; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X | 0 | Amenity - Drawings + Coord |  |  |  | 2023-05-26 |  | IFC BG IFC | Dated 230526 / Uploaded 230529 | SM | X
1712A | HAWKSLEY - Amen | CODE: BP rev; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X | 0 | Amenity - Details |  |  |  | 2023-06-08 |  | Con Startup mtg
1712A | HAWKSLEY - Amen | CODE: SPEC; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X; S: X | 0 | Amenity - Spec |  |  |  | 2023-06-21 |  | Construction Start - Approx (Pouring crane pad lean mix @ Hawksley client event)
1712A | HAWKSLEY - Amen | [32 empty] | 0 | Amenity - CA |  |  |  | 2023-08-04 |  | IFC Above Grade | Dated 230804 / Uploaded 230808 | bar: S; S to S; S to S; S to S; S to S
1712A | HAWKSLEY - Amen | CODE: EXTR; S: X; S: X; S: X; S: X; S: X; T: 2.5; S: X; S: X; S: X; S: X; T: 2.5 | 5 | Amenity - EXTRA
0 | bar: S; S to S; S to S; S to S; S to S
| HAWKSLEY - RVT | S: X; S: X; S: X; T: 1.5; S: X; S: X; S: X; S: X; T: 1; S: X; S: X | 2.5 | REVIT model cleanup + Learning
| subtotal |  | 0 | 0 | 7.5 | 5 | 7.5 | 7.5 | 0 | 0 | 0 | 7.5 | 6.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 4 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 6.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 142
STAT. HOLIDAY |  | M: 7.5; M: 7.5 | 15 |  |  |  |  | Focus / Activities this Month
ADMIN /GENERAL |  | W: 2.5; W: 1; W: 1.5; W: 1 | 6 | Filing, Cleanup/Move, Time, Other |  |  |  | 1712 - CA progress / Construction
PROMOTION | [33 empty] | 0 |  |  |  |  | Status |  | CA
PROFESSIONAL DEVELOPMENT | [33 empty] | 0 |  | Other |  |  | Design / Coord |  | P3 ramp / P2 Ramp Outside |  | SD | Elevator - SD review / comm w. TKE/NE re transformer rm rqts
PROFESSIONAL DEV - UNPAID | [35 empty] | 0 |  |  |  |  | Structural markups |  |  | West Tower Windows
ILLNESS | [33 empty] | 0 | [6 empty] | Electrical shafts - correction to Eclosets / update RWA slab openings |  |  | Frame Colour samples
VACATION | [33 empty] | 0 | Days Remaining: 3 (2021) / 25 (2022) / 25 (2023) | [5 empty] | Mech / struct trench coord
OTHER - WG REVIT Standards | [33 empty] | 0 | Meetings / Organization / Review / Development | 0 |  |  |  |  | Transformer Rm / Mech ducts / Standpipe / Transformers |  | SI | ASI 011 / ASI 012Slab plans - P3 , L1/P2
OTHER - REVIT Details | [33 empty] | 0 |  | 0 |  |  |  |  | Column alignment @ L7 & 8 |  |  | ASI 010 - MSI 003 / ESI 006 - Trench drain to CB's
OTHER - WG Std Dets & Dwgs | [33 empty] | 0 |  | 0 |  |  |  |  | L2 West conc @ window opening / zone steel
OTHER - WG Contract Admin | [35 empty] | 0 | [6 empty] | RFI | RFI 030 - Stair E elevations
OTHER - WG Specification | [33 empty] | 0 |  | 0 |  |  | Site Changes |  | P3 Trench Drain |  |  | RFI 032 - Mech recess location
OTHER - WG Sustainability | [33 empty] | 0 | Meetings + Prep / K drive cleanup / other uploads for site | 0 |  |  |  |  | L1 to P3 ramp |  |  | RFI 035 - SW window discrepancy w/ structural
OTHER - Software | [33 empty] | 0 |  | 0 | [7 empty] | RFI 036 - Water bottle station (spec & drain)
OTHER - Associate + Partner mtgs | [33 empty] | 0 |  | 0 | [7 empty] | RFI 038 - Elev transformer rm knockouts / Mech ducts
OTHER - Product Info | [33 empty] | 0 |  |  |  |  | EXTRAS |  |  |  |  | RFI 039 - Zone Steel in west Core
total |  |  | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 5.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 163 |  | 0
[39 empty] | AMENITY |  |  |  | WG - Working Groups
WORK CODES: | [38 empty] | Status | Redesign Startup meeting - 23.09.29. Redesign will be by Saunders |  |  | Sustainability | Re-Startup Meeting - 23.09.20
D | Pre-DP or schematic design / investigation | T: ADM; T: Construction administration / site services; S: Enter no of paid days in square; M: 22 | 165 | [5 empty] | Bi-monthly meetings moving forward |  |  |  | Regroup: Focus on: WG/RWA Goals, Materials, Step Code Summary, PH Model
DP | DP Drawings | T: EXTR; T: Extra services beyond contract - SEE EXTRA SERVICE FORM | [10 empty] | Meetings will be every 2 weeks following
BP | Building permit | T: SPEC; T: Specification; S: Flextime (Timeoff) this month | -2 | Specify for each project above |  |  |  | Action | Updated contract by AS / or Hourly Extras?
WD | Working drawings | T: TEND; T: Tendering phase | [6 empty] | Waiting for saunders design or questions |  |  | REVIT Template | Review
MOD | Model Making | T: CON; T: Construction phase - drawing details during construction and; S: Flextime (Timeoff) beginning of month | 590.5 | [9 empty] | Request project list, status, startup, questions
MK | Marketing | T: coordination of these that should have been done before tender | [5 empty] | Schedule | Revised IFBP |  | 2023-12-08
|  | S: Flextime (Timeoff) end of month | 588.5 | [5 empty] | Revised IFT |  | 2023-12-15 (TBC)
[36 empty] | 2021 | 2022 | 2023
[36 empty] | 13 | 25 | 25 | Start of Month
[36 empty] | 10 |  |  | This Month
[36 empty] | 3 | 25 | 25 | End of Month
Note on F8: Andrea Bolin: Personelle discussion
Note on F10: Andrea Bolin: ConsultantTeam Mtg
Note on H10: Andrea Bolin: Landscape Drainage Meeting
Note on I10: Andrea Bolin: Mtg w. Siber + Prep + F/U
Note on O10: Andrea Bolin: MH - Wendell details
Note on P10: Andrea Bolin: IC - re. ramp slopes at driveway
Note on T10: Andrea Bolin: ConsultantTeam Mtg Mtg w. PC re. Drains
Note on W10: Andrea Bolin: GS meeting
Note on AB10: Andrea Bolin: BH - Ella re. colour samples
Note on AD10: Andrea Bolin: BL - NS & re. Slab Plans PC re. MSI003
Note on AG10: Andrea Bolin: NE - prep + mtg Rated risers - clarification & correction of NE dwgs & RWA slab plans
Note on AH10: Andrea Bolin: ConsultantTeam Mtg
Note on T20: Andrea Bolin: 1712A mtg & follow up w. dwgs & email
Note on AH20: Andrea Bolin: 1712A mtg & follow up w. dwgs & email