## Sheet1
[36 empty] | 9704 | Thompson's Landing
[36 empty] | 9713 | Carrington
[12 empty] | NAME |  | Al Mitchell | [15 empty] | MONTH / YR |  |  |  |  | April 2024 | 9714 | Carrington Enclave
[36 empty] | 9927 | 3580 West 41st
PROJECT | [35 empty] | 9930 | UBC Earthquake
NO. | NAME | WORK | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | TOTAL | DESCRIPTION / COMMENTS | 0002 | Skyland Meadows
|  | CODE | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T |  |  |  | 0031 | Macvey
[34 empty] | 0 |  | 0038 | UBC Bldg C | bar: 6 S to 7 S; 13 S to 14 S; 20 S to 21 S; 27 S to 28 S
2009 | Sooke Church Rd | CA | [31 empty] | 4 | Occupancy documents + prep | 0219 | Palladium | bar: 1 M to 30 T
2009 | Sooke Church Rd | CA | 1 | 2 | 1 | 1 | 1 | X | X | 1 | 1 | 2 | 1 | 2 | X | X | 2 | 1 | 1 | 1 |  | X | X | 1 | 1 | 1 |  | 1 | X | X | 1 | 1 |  | 24 | General Contract Admin | 0225 | Allard site
2009 | Sooke Church Rd | WD | [31 empty] | 0 | BP / IFC Dwgs | 0234 | UBD Intracorp | bar: 1 M to 30 T
2009 | Sooke Church Rd | CA | [31 empty] | 1 | Arch S/I's | 0236 | Dongli Lake | bar: 1 M; 6 S to 7 S; 13 S to 14 S; 20 S to 21 S; 27 S to 28 S
2009 | Sooke Church Rd | CA | [31 empty] | 1 | RFI's | 0243 | D & J Ind office | bar: 1 M to 30 T
2009 | Sooke Church Rd | CA | [31 empty] | 1 | Site Reviews + reports | 0245 | Design Studio Reno | bar: 6 S to 7 S; 13 S to 14 S; 18 T; 20 S to 21 S; 27 S to 28 S
2009 | Sooke Church Rd | CA | [31 empty] | 1 | Site Meetings (virtual via Teams) | 0249 | Klahanie Townhouses | bar: 1 M to 5 F; 7 S to 12 F; 14 S to 19 F; 21 S to 26 F; 28 S to 30 T
2009 | Sooke Church Rd | CA | 6 S: X; 7 S: X; 9 T: 12; 13 S: X; 14 S: X; 20 S: X; 21 S: X; 27 S: X; 28 S: X |  | 12 | Site Meetings + Reviews (on site) | 0254 | 1117 Pendrell St
2009 | Sooke Church Rd | CA | [31 empty] | 1 | Shop drawings | 0305 | British Prop - Lot 64 | bar: 1 M to 30 T
2009 | Sooke Church Rd | CA | [31 empty] | 5 | Radon gas remediation | bar: 6 S to 7 S; 11 T; 13 S to 14 S; 16 T to 17 W; 20 S to 21 S; 24 W to 25 T; 27 S to 28 S
2017 | Lynn Townhomes | CA | 4 T: 3; 6 S: X; 7 S: X; 13 S: X; 14 S: X; 20 S: X; 21 S: X; 27 S: X; 28 S: X |  | 3 | Site Visit - Contract Admin (Emery Lot 3)
2017 | Lynn Townhomes | CA |  |  | 1 | 1 | 1 | X | X |  |  | 2 | 2 | 1 | X | X | 1 |  | 2 | 1 | 1 | X | X |  |  |  |  | 1 | X | X |  |  |  | 14 | General Contract Admin (Emery Lot 3)
0 | bar: 1 M to 30 T
| subtotal |  | 3 | 2 | 3 | 5 | 2 | 0 | 0 | 2 | 13 | 4 | 4 | 3 | 0 | 0 | 3 | 2 | 4 | 3 | 1 | 0 | 0 | 1 | 3 | 4 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 67 |  |  | invalid
STAT. HOLIDAY | [33 empty] | 0
ADMIN /GENERAL | [33 empty] | 0
PROMOTION | [33 empty] | 0
PROFESSIONAL DEVELOPMENT | [33 empty] | 0
PROFESSIONAL DEV - UNPAID
ILLNESS | [33 empty] | 0
VACATION | [33 empty] | 0
OTHER - Please specify | [33 empty] | 0
OTHER - Please specify | [33 empty] | 0
total |  |  | 3 | 2 | 3 | 5 | 2 | 0 | 0 | 2 | 13 | 4 | 4 | 3 | 0 | 0 | 3 | 2 | 4 | 3 | 1 | 0 | 0 | 1 | 3 | 4 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 67
WORK CODES:
FEA | Feasibility Studies |  | 3 W: WD; 5 F: Working drawings; 27 S: Enter no of paid days in square
D | Pre-DP or schematic design / investigation |  | 3 W: SPEC; 5 F: Specifications
RZ | Rezoning |  | 3 W: TEND; 5 F: Tendering; 27 S: Flextime (Timeoff) this month |  |  | Specify for each project above
DP | Development permit drawings |  | 3 W: EXTR; 5 F: Extra Services beyond contract - SEE EXTRA SERVICES FORM
BP | Building permit drawings |  | 3 W: CA; 5 F: Construction administration / site services; 27 S: Flextime (Timeoff) beginning of month
Flextime (Timeoff) end of month