## Sheet1
[14 empty] | NAME |  | Andrea Bolin | [15 empty] | MONTH / YR |  |  | November 2022
PROJECT
NO. | NAME | WORK | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | TOTAL | DESCRIPTION / COMMENTS
|  | CODE | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
0 | bar: 5 S to 6 S; 12 S to 13 S; 19 S to 20 S; 26 S to 27 S
1508 | COURTENAY | CA | 1 T: 0.5; 3 T: 0.5; 5 S: X; 6 S: X; 9 W: 0.5; 12 S: X; 13 S: X; 15 T: 0.5; 17 T: 2; 19 S: X; 20 S: X; 21 M: 2; 22 T: 0.5; 26 S: X; 27 S: X; 28 M: 0.5; 30 W: 0.5 |  | 7.5 | Proj Admin (occupancy docs)
1508 | COURTENAY | CA | 4 F: 0.5; 5 S: X; 6 S: X; 7 M: 5.5; 8 T: 2; 12 S: X; 13 S: X; 19 S: X; 20 S: X; 26 S: X; 27 S: X; 30 W: 2 |  | 10 | SD / SI / RFI - see log (FO + Issues) + Site comm /mtgs
1508 | COURTENAY | CA | [31 empty] | 0 | Details | bar: 1 T to 30 W
1508 | COURTENAY | OCC | 3 T: 1; 5 S: X; 6 S: X; 12 S: X; 13 S: X; 14 M: 1; 16 W: 3; 19 S: X; 20 S: X; 25 F: 6; 26 S: 1; 27 S: 2 |  | 14 | Occ inc site visit w. DR
1712 | HAWKSLEY | IFT | 1 T: 0.5; 2 W: 0.5; 4 F: 0.5; 5 S: X; 6 S: X; 9 W: 0.5; 10 T: 2; 12 S: X; 13 S: X; 19 S: X; 20 S: X; 21 M: 1; 26 S: X; 27 S: X; 28 M: 0.5; 30 W: 1 |  | 6.5 | Proj Admin (Billing, Printing, Uploads, Mtg Sched, General) / client
1712 | HAWKSLEY | IFT | 2 | 3 | 5.5 | 3 | X | X | 2 | 2 | 3 | 3 | 1 | 3 | X | 3 | 1.5 | 1 | 1 |  | X | X | 1 | 2 | 3 | 3 | 1 | X | X | 2 | 2 | 2 |  | 50 | IFT Building Drawings, Coord + mtgs
1712 | HAWKSLEY | BP | 2 | 5 |  | 3 | X | X | 1 | 2 | 3 | 3 | 1 | X | 3 | 3 | 1.5 | 1 | 1.5 | 3 | X | X |  | 3 | 4 | 4 | 1 | X | X | 2 | 2 | 1 |  | 50 | BP Comments + changes
1712 | HAWKSLEY | IFT | [31 empty] | 0 | Details | bar: 5 S to 6 S; 12 S to 13 S; 19 S to 20 S; 26 S to 27 S
1712 | HAWKSLEY | IFT | 5 S: X; 6 S: X; 8 T: 2; 12 S: X; 13 S: X; 15 T: 2; 17 T: 2; 18 F: 3; 19 S: X; 20 S: X; 21 M: 2; 24 T: 1; 25 F: 1; 26 S: X; 27 S: X; 28 M: 3 |  | 16 | Amenity - Drawings + Coord
1712 | HAWKSLEY | IFT | 5 S: X; 6 S: X; 8 T: 1; 12 S: X; 13 S: X; 14 M: 1; 17 T: 1; 18 F: 2; 19 S: X; 20 S: X; 21 M: 2; 23 W: 0.5; 26 S: 1; 27 S: 3; 28 M: 0.5; 29 T: 3; 30 W: 0.5 |  | 15.5 | Spec
1712 | HAWKSLEY - EXT Win | EXTRA | 1 T: 4; 3 T: 1; 4 F: 1; 5 S: 4; 6 S: 4; 9 W: 1.5; 12 S: X; 13 S: X; 15 T: 1; 19 S: X; 20 S: X; 26 S: X; 27 S: X |  | 16.5 | Extra - Alt Windows
1712 | HAWKSLEY - EXT Stair A/B Exit | EXTRA | 5 S: X; 6 S: X; 12 S: X; 13 S: X; 19 S: X; 20 S: X; 24 T: 0.5; 26 S: X; 27 S: X; 29 T: 1 |  | 1.5 | Extra - Files to francl - calls coord
1712 | HAWKSLEY - RVT |  | 5 S: X; 6 S: X; 12 S: X; 13 S: X; 16 W: 2; 19 S: X; 20 S: X; 22 T: 2; 26 S: X; 27 S: X; 30 W: 2 |  | 6 | REVIT model cleanup + Learning
| subtotal |  | 9 | 8.5 | 8 | 8 | 4 | 4 | 8.5 | 9 | 8.5 | 8 | 2 | 3 | 3 | 8 | 6.5 | 7 | 7.5 | 8 | 0 | 0 | 8 | 7.5 | 7.5 | 8.5 | 9 | 2 | 5 | 8.5 | 8 | 9 | 0 | 193.5
STAT. HOLIDAY |  |  | 11 F: 7.5 |  | 7.5
ADMIN /GENERAL | [33 empty] | 2 | Filing, Cleanup/Move, Time, Other | bar: 15 T to 16 W
PROMOTION | [33 empty] | 0
PROFESSIONAL DEVELOPMENT | [33 empty] | 0
PROFESSIONAL DEV - UNPAID
ILLNESS | [33 empty] | 0
VACATION | [33 empty] | 0 | Days Remaining: 5 (2020) / 25 (2021) / 25 (2022)
OTHER - REVIT Standards | [33 empty] | 0 | Meetings / Organization / Review / Development
OTHER - REVIT Details | [33 empty] | 0
OTHER - Std Assbl's Dets Gen Notes | [33 empty] | 0
OTHER - Contract Admin Mtg | [33 empty] | 0
OTHER - Associates Mtg / Minutes | [33 empty] | 0
OTHER - Intranet Reorganization | [33 empty] | 0 | Meetings + Prep / K drive cleanup / other uploads for site
OTHER - Sustainability | [33 empty] | 0
OTHER - Staff reviews + interviews | [33 empty] | 0
OTHER - Associate + Partner mtgs | [33 empty] | 2 | bar: 1 T; 29 T
total |  |  | 9 | 8.5 | 8 | 8 | 4 | 4 | 8.5 | 9 | 8.5 | 8 | 9.5 | 3 | 3 | 8 | 7.5 | 8 | 7.5 | 8 | 0 | 0 | 8 | 7.5 | 7.5 | 8.5 | 9 | 2 | 5 | 8.5 | 8 | 9 | 0 | 205
WORK CODES:
D | Pre-DP or schematic design / investigation |  | 3 T: ADM; 5 S: Construction administration / site services; 29 T: Enter no of paid days in square; 30 W: 22 |  | 165
DP | DP Drawings |  | 3 T: EXTR; 5 S: Extra services beyond contract - SEE EXTRA SERVICE FORM
BP | Building permit |  | 3 T: SPEC; 5 S: Specification; 29 T: Flextime (Timeoff) this month |  | 40 | Specify for each project above
WD | Working drawings |  | 3 T: TEND; 5 S: Tendering phase
MOD | Model Making |  | 3 T: CON; 5 S: Construction phase - drawing details during construction and; 29 T: Flextime (Timeoff) beginning of month |  | 424.5
MK | Marketing |  | 5 S: coordination of these that should have been done before tender
|  |  | 29 T: Flextime (Timeoff) end of month |  | 464.5
Note on R7: Andrea Bolin: dr / cf /parking + section
Note on T7: Andrea Bolin: spray insul / system 15 /
Note on X7: Andrea Bolin: stair H inquiry
Note on AE7: Andrea Bolin: upper landing guards
Note on J8: Andrea Bolin: parking encroachment details lobby cladding discussions w. DR
Note on K8: Andrea Bolin: lobby area / other
Note on AG8: Andrea Bolin: glass canopy
Note on S10: Andrea Bolin: change 0 signing suthority
Note on AB10: Andrea Bolin: occ dry run
Note on AC10: Andrea Bolin: site visit photos + notes
Note on AD10: Andrea Bolin: site visit comments
Note on M11: Andrea Bolin: filing VV BL mtg
Note on X11: Andrea Bolin: lobby walk off
Note on AE11: Andrea Bolin: bl mtg
Note on J12: Andrea Bolin: LS / dwv updates
Note on M12: Andrea Bolin: LS grades / Base plans out - East
Note on Q12: Andrea Bolin: code mtg / LS plan / Lobby sections
Note on R12: Andrea Bolin: consultanat mtg
Note on AE12: Andrea Bolin: drainage mtg
Note on AF12: Andrea Bolin: ID coord consultant coord - team mtg + iD
Note on AG12: Andrea Bolin: lobby vents - plan updates
Note on K13: Andrea Bolin: code compliance mtg
Note on U13: Andrea Bolin: review safer home + buildt green reqts
Note on Z13: Andrea Bolin: write dwv response / review mech
Note on AB13: Andrea Bolin: bases to GHL
Note on K15: Andrea Bolin: wood cladding
Note on U15: Andrea Bolin: changesto spa
Note on X15: Andrea Bolin: changesto stairs / tactile warning
Note on AB15: Andrea Bolin: changesto millwork / core
Note on AE15: Andrea Bolin: chnages to amen core
Note on AC16: Andrea Bolin: read res spec
Note on AD16: Andrea Bolin: read res spec
Note on AF16: Andrea Bolin: review on zoom w gm
Note on D17: Andrea Bolin: Siber details - metgn + fu
Note on F17: Andrea Bolin: hours + fees
Note on G17: Andrea Bolin: hours + fees
Note on H17: Andrea Bolin: lower sills on windows - w
Note on I17: Andrea Bolin: lower sills on windows - e
Note on L17: Andrea Bolin: windows - info to MH
Note on R17: Andrea Bolin: siber windor hours
Note on S22: Andrea Bolin: extras billing to bn