## feb 24
Name: | Liam Gillis
Date | Total Hourse |  | Hours | Category |  | Description
2024-02-06 | 0.5 |  | 0.5 | RFI | Responding to site question concerning the size and alignment of the TH patio doors
2024-02-07 | 1 |  | 1 | RFI | Responding to site question concerning the colour and handling of the TH exterior doors
2024-02-08 | 2 |  | 2 | RFI | Responding to site question concerning the slope at routing of SFD entry paths from the street
2024-02-09 | 0.5 |  | 0.5 | RFI | Responding to site question concerning the SFD interior handrails
2024-02-12 | 6.5 |  | 2.5 | Design | Reviewing garage roof vent calculations
|  |  | 1 | Admin | Reviewing outstanding items list
|  |  | 3 | Design | Reviewing TH rear guardrails layouts and clearances
2024-02-13 | 13.5 |  | 13.5 | Site Visit | -
2024-02-14 | 1 |  | 1 | SD | TH exterior door R3 shop drawings
2024-02-27 | 1.5 |  | 1.5 | Meeting | Reviewing roof ventilation and other site issues with Adam Jarolim
TOTAL | 26.5
Name: | Paria Moghaddam
Date | Total Hourse |  | Hours | Category |  | Description
2024-02-01
2024-02-06 | 1 |  |  | Admin | letter for CRP change
2024-02-07 | 0.5 |  |  | Filing / Admin | filing emailed docs/ Booking ferry
2024-02-08 | 0.5 |  |  | Logs | updating SD+SI+ RFI logs
2024-02-12 | 0.5 |  |  | Logs | updating SD+SI+ RFI logs
2024-02-15 | 1 |  |  | SD Coordination | TH exterior door shop drawings R3
2024-02-16 | 1 |  |  | Site Review | Site Review #12
2024-02-20 | 0.5 |  |  | SD Coordination | TH exterior door shop drawings R3
2024-02-23 | 0.5 |  |  | Filing / Admin | filing / Booking ferry
2024-02-26 | 0.5 |  |  | Logs | updating SD+SI+ RFI logs
TOTAL | 6
Name: | Alan Mitchel
Date | Total Hourse |  | Hours | Category |  | Description
2024-02-01
2024-02-01 |  |  | 3 | review reports | Outstanding Items list
2024-02-02 |  |  | 2 | reports + design | outstanding Items + entry stair width
2024-02-05 |  |  | 3 | reports + design | Outstanding Items list + entry stair width
2024-02-06 |  |  | 1 | RFI / design | deck door + window head alignment
2024-02-07 |  |  | 2 | fire blocking + list | review of photos from Larry + review of structural + mech comments on arch outstanding items list
2024-02-08 |  |  | 1 | design / sidewalks | discussion of conflicts between infrastructure + sidewalk layout
2024-02-09 |  |  | 1 | design / BCBC | request for BCBC requirements re: handrails from site / construction
2024-02-12 |  |  | 1 | fireblocking mock-up | marked-up photos from other projects showing fireblocking mock-ups we need
2024-02-13 |  |  | 13 | site meeting / visit | site visit + photo download
2024-02-14 |  |  | 3 | site visit follow-up | site review report / marked-up site photos / deck board confirmation
2024-02-15 |  |  | 3 | contract admin | TH : VB/AB tie ins / marked-up photos issued / deck board confirmation
2024-02-16 |  |  | 2 | site review report | site review report #12/ marked-up fireblocking photos re-issued
2024-02-20 |  |  | 1 | contract admin | air barrier continuity w/ JRS
2024-02-21 |  |  | 1 | contract admin | outstanding items list follow-up
2024-02-22 |  |  | 1 | contract admin | attic venting
2024-02-27 |  |  | 3 | contract admin | attic venting zoom meeting w/ JRS
2024-02-28 |  |  | 4 | contract admin | TH bedroom window review / soffit venting details / rain chain
Total | 45
DDR REDUCED AM HOURS TO 29.5 hours on this bill
Name: | Rylan Basi
Date | Total Hourse |  | Hours | Category |  | Description
2024-02-01
2024-02-03 |  |  | 11 | Site Visit
2024-02-25 |  |  | 2 | Admin | Arch Site Report #13
Total | 13
DDR REDUCED Ryan HOURS TO 0 (zero) hours on this bill

## Jan 24
Liam Gillis
2024-01-01
2024-01-02 | 1 |  | 1 | SD | Reviewing Window SDs
2024-01-09 | 0.5 |  | 0.5 | Meeting | Sooke internakl meeting with Stanley and Mitch
2024-01-15 | 0.5 |  | 0.5 | RFI | Reviewing a question from site regarding what types of railings we have at various locations.
2024-01-16 | 12 |  | 12 | site visit | –
2024-01-17 | 3 |  | 2 | Site instruction | Draft Site instruction 38 - Th party wall fireblocking
|  |  | 1 | Design | Reviewing color schemes for alternate SFD door colours
2024-01-18 | 1.5 |  | 0.5 | RFI | Response to SI regarding conflict with TH entry door
|  |  | 1 | Design | Reviewing colour shcemes for alternate SFD colours
2024-01-19 | 4 |  | 1 | Site instruction | Site instruction 38 - Th party wall fireblocking
|  |  | 3 | Site instruction | DRAFT Site Instruction 39 - TH Entry Door Sidelight Update
2024-01-22 | 3 |  | 1 | Site instruction | Site Instruction 38 - TH Entry Door Sidelight Update
|  |  | 2 | Design | Sending out proposal for alternate SFD door colours to Lenny
2024-01-23 | 3.5 |  | 0.5 | SD | Finalizing and sending out window show drawings
|  |  | 0.5 | Meeting | Sooke Internal Meeting with Stanley and Mitch
|  |  | 2 | RFI | Reviewing a SFD hot water tank flue with Mechanical and Envelope
|  |  | 0.5 | Meeting | Lengthy discussion with Envelop Consultant :l: via email and phone regarding ongoing poor follow up on site
2024-01-24 | 5.5 |  | 1.5 | RFI | Reviewing a SFD hot water tank flue with Mechanical and Envelope
|  |  | 4 | Design | Reviewing TH roof vent calculations
2024-01-25 | 3 |  | 2 | Site instruction | DRAFT Site Instruction 38 - TH Entry Door Sidelight Update - REVISION 01
|  |  | 1 | RFI | response to site question about structure at TH entries
2024-01-26 | 2 |  | 2 | RFI | response to site insrtuction question about structure
2024-01-29 | 2.5 |  | 2.5 | Design | Reviewing and confirming SFD roof vent calculation
2024-01-30 | 4.5 |  | 4.5 | Site instruction | Site instruction 40 - TH Entry Stair update
TOTAL | 46.5 |  | hrs
Paria Moghaddam |  |  | LOG / SD SI disrtibution and coordination with consultants
2024-01-01
2024-01-10 | 0.5 |  |  | Filing / Admin
2024-01-11 | 0.5 |  |  | SD Coordination | TH Tripled Glaze
2024-01-12 | 0.5 |  |  | Logs | updating SD+SI+ RFI logs / TH SD
2024-01-15 | 1 |  |  | Logs / filing | updating SD+SI+ RFI logs / TH SD
2024-01-16 | 1 |  |  | Logs / filing | updating SD+SI+ RFI logs / TH SD
2024-01-17 | 1 |  |  | Logs / filing | updating SD+SI+ RFI logs / TH SD
2024-01-18 | 1 |  |  | Logs / filing | updating SD+SI+ RFI logs / TH SD
2024-01-19 | 0.5 |  |  | Logs / filing | updating SD+SI+ RFI logs / ASI # 38
2024-01-22 | 1 |  |  | Logs / filing | updating SD+SI+ RFI logs / TH SD / ASI #39
2024-01-23 | 0.5 |  |  | Logs / filing | updating SD+SI+ RFI logs / TH SD
2024-01-24 | 0.5 |  |  | Filing | filing emailed docs
2024-01-25 | 0.5 |  |  | Logs / filing | updating SD+SI+ RFI logs / filing emailed docs
2024-01-29 | 1 |  |  | Logs
2024-01-30 | 0.5 |  |  | Logs
TOTAL | 10 |  | hrs
Al Mitchell
2024-01-01
2024-01-02 |  |  | 1 | contract admin | Christmas catch-up
2024-01-03 |  |  | 1 | contract admin | window test report review / triple glazed option
2024-01-04 |  |  | 1 | contract admin | window test report review
2024-01-09 |  |  | 0.5 | contract admin | RWA internal review mt'g w/ Stanley + Liam / reminders for tub + shower issues
2024-01-12 |  |  | 2 | RFI | options for fire blocking at off set floor + landing levels / follow-up w/ structural site review report
2024-01-15 |  |  | 1 | contract admin | prep for site meeting
2024-01-16 |  |  | 12 | site meeting / visit | site meeting + review
2024-01-17 |  |  | 2 | contract admin | site meeting photos + review follow-ups / front entry + stair conflicts
2024-01-18 |  |  | 1 | site review report | arch site review report reviewed
2024-01-19 |  |  | 2 | envelope site review | garage window install detailing discussions + arch site review report reviewed + issued
2024-01-22 |  |  | 1 | contract admin | missing roof vents reminder
2024-01-23 |  |  | 2 | contract admin | mitigation of hwt exhaust at main roof soffit
2024-01-24 |  |  | 1 | contract admin | coord for mitigation of hwt exhaust at main roof soffit + roof vent calcs
2024-01-26 |  |  | 3 | contract admin | arch s/I 38 r1 review / patio access door vs window head ht's / follow-ups for JRS report + issues
2024-01-30 |  |  | 2 | contract admin | door colours / Arch outstanding action items list review with DDR
2024-01-31 |  |  | 2 | contract admin | TH wide stair review
Total | 34.5 |  | hr
DDR REDUCED AM HOURS TO 22 hours on this bill
Rylan
2024-01-01
2024-01-16 |  |  | 11 | Site Visit
2024-01-18 |  |  | 2.5 | Admin | Arch Site Report #11
2024-01-19 |  |  | 1 | Admin | Sooke Internal Meeting
Total | 14.5