## January 2024
January 2024 Time and Tasks
Liam Gillis
Date | Total Hours | Hours | Category |  | Description
2024-01-01
2024-01-02 | 1 | 1 | SD | Reviewing Window SDs
2024-01-09 | 0.5 | 0.5 | Meeting | Sooke internakl meeting with Stanley and Mitch
2024-01-15 | 0.5 | 0.5 | RFI | Reviewing a question from site regarding what types of railings we have at various locations.
2024-01-16 | 12 | 12 | site visit | –
2024-01-17 | 3 | 2 | Site instruction | Draft Site instruction 38 - Th party wall fireblocking
|  | 1 | Design | Reviewing color schemes for alternate SFD door colours
2024-01-18 | 1.5 | 0.5 | RFI | Response to SI regarding conflict with TH entry door
|  | 1 | Design | Reviewing colour shcemes for alternate SFD colours
2024-01-19 | 4 | 1 | Site instruction | Site instruction 38 - Th party wall fireblocking
|  | 3 | Site instruction | DRAFT Site Instruction 39 - TH Entry Door Sidelight Update
2024-01-22 | 3 | 1 | Site instruction | Site Instruction 38 - TH Entry Door Sidelight Update
|  | 2 | Design | Sending out proposal for alternate SFD door colours to Lenny
2024-01-23 | 3.5 | 0.5 | SD | Finalizing and sending out window show drawings
|  | 0.5 | Meeting | Sooke Internal Meeting with Stanley and Mitch
|  | 2 | RFI | Reviewing a SFD hot water tank flue with Mechanical and Envelope
|  | 0.5 | Meeting | Lengthy discussion with Envelop:l: via email and phone regarding ongoing poor workmanship on site
2024-01-24 | 5.5 | 1.5 | RFI | Reviewing a SFD hot water tank flue with Mechanical and Envelope
|  | 4 | Design | Reviewing TH roof vent calculations
2024-01-25 | 3 | 2 | Site instruction | DRAFT Site Instruction 38 - TH Entry Door Sidelight Update - REVISION 01
|  | 1 | RFI | response to site question about structure at TH entries
2024-01-26 | 2 | 2 | RFI | response to site insrtuction question about structure
2024-01-29 | 2.5 | 2.5 | Design | Reviewing SFD roof vent calculation
2024-01-30 | 4.5 | 4.5 | Site instruction | Site instruction 40 - TH Entry Stair update
TOTAL | 46.5
Name: | Paria Moghaddam
Date | Total Hourse | Hours | Category |  | Description
2024-01-01
TOTAL
Doug Ramsay
Date | Total Hours | Hours | Category |  | Description
2024-01-01
| 2 |  |  | Reviewing Window of Code retaied and astethic issues
Alan Mitchel
Date | Total Hours | Hours | Category |  | Description
2024-01-01
Rylan Bai
Date | Total Hours | Hours | Category |  | Description
2024-01-01

## February 2024
Name: | Paria Moghaddam
Date | Total Hourse | Hours | Category |  | Description
2024-02-01
2024-02-06 | 1 |  | Admin | letter for CRP change
2024-02-07 | 0.5 |  | Filing / Admin | filing emailed docs/ Booking ferry
2024-02-08 | 0.5 |  | Logs | updating SD+SI+ RFI logs
2024-02-12 | 0.5 |  | Logs | updating SD+SI+ RFI logs
2024-02-15 | 1 |  | SD Coordination | TH exterior door shop drawings R3
2024-02-16 | 1 |  | Site Review | Site Review #12
2024-02-20 | 0.5 |  | SD Coordination | TH exterior door shop drawings R3
2024-02-23 | 0.5 |  | Filing / Admin | filing / Booking ferry
Total | 5.5
Doug Ramsay
Date | Total Hours | Hours | Category |  | Description
2024-02-01
| 1.5 |  |  | Reviewing Window of Code retaied and astethic issues